## Client_Onboarding
Process Name | Client On-boarding
Document date | 2017-04-10
[5 empty] | SOLUTION DESIGN | [8 empty] | BUILD | [8 empty] | TESTING
ID | Sub-process Name (Activity ) | ID | WBS Activities | Priority | AS IS Process Maps & Detailing |  |  | Video recording |  |  | PDD |  |  | Handover to Dev |  |  | Test Scenarios |  |  | Test Data Definition |  |  | UAT plan |  |  | Testing |  |  | User manuals |  |  | Training |  |  | Lessons Leaned |  |  | Handover Documentation
[5 empty] | Status | Baseline Due Date | Actual Delivery Date | Status | Baseline Due Date | Actual Delivery Date | Status | Baseline Due Date | Actual Delivery Date | Status | Baseline Due Date | Actual Delivery Date | Status | Baseline Due Date | Actual Delivery Date | Status | Baseline Due Date | Actual Delivery Date | Status | Baseline Due Date | Actual Delivery Date | Status | Baseline Due Date | Actual Delivery Date | Status | Baseline Due Date | Actual Delivery Date | Status | Baseline Due Date | Actual Delivery Date | Status | Baseline Due Date | Actual Delivery Date | Status | Baseline Due Date | Actual Delivery Date
A | Client identification | A.01.01 | Collect necessary documents & forms - Client type A | High | Finalised | 2017-02-10 | 30/09/2017 | Finalised | 15/09/2017 | 15/09/2017 | WIP | 13/10/2017 |  | Not started | 16/10/2017 |  | Not started | 18/10/2017 |  | Not started |  |  | Not started | 25/10/2017 |  | Not started | 2017-01-11 |  | Not started | 2017-03-11 |  | Not started | 2017-09-11 |  | Not started | 20/11/2017 |  | Not started | 20/11/2017
|  | A01.02 | Collect necessary documents & forms - Client typeB | High | Under validation with SME | 2017-02-10 | [10 empty] | Not started | 18/10/2017 |  | Not started | [5 empty] | Not started | 2017-01-11 |  | Not started | 2017-03-11
|  | A.02 | Verify data | High | Under validation with SME | 2017-03-10 |  | Finalised | 15/09/2017 | 15/09/2017 | [6 empty] | Not started | 18/10/2017 |  | Not started | [5 empty] | Not started | 2017-01-11 |  | Not started | 2017-03-11
|  | A.03 | Accept/ reject request | High | Under validation with SME | 2017-03-10 |  | Finalised | 15/09/2017 | 15/09/2017 | [6 empty] | Not started | 20/10/2017 |  | Not started | [5 empty] | Not started | 2017-03-11 |  | Not started | 2017-06-11
|  | A.04 | Exception 1 | Medium | Under validation with SME | 2017-03-10 |  | Finalised | 15/09/2017 | 15/09/2017 | [6 empty] | Not started | 20/10/2017 |  | Not started | [5 empty] | Not started | 2017-03-11 |  | Not started | 2017-06-11
|  | A.05 | Exception 2 | Medium | Under validation with SME | 2017-03-10 |  | Finalised | 15/09/2017 | 15/09/2017 | [6 empty] | Not started | 20/10/2017 |  | Not started | [5 empty] | Not started | 2017-03-11 |  | Not started | 2017-06-11
B | Open Client | B.01 | Introduce Client data in app A | High | WIP | 2017-05-10 |  | Finalised | 16/09/2017 | 16/09/2017 | [6 empty] | Not started | 20/10/2017 |  | Not started | [5 empty] | Not started | 2017-03-11 |  | Not started | 2017-06-11
|  | B.02 | Introduce Client data in app A | High | WIP | 2017-05-10 |  | Finalised | 16/09/2017 | 16/09/2017 | [6 empty] | Not started | 20/10/2017 |  | Not started | [5 empty] | Not started | 2017-03-11 |  | Not started | 2017-07-11
C | Open Account | C.01 | Open client account in the dedicated app | Medium | WIP | 2017-06-10 |  | Finalised | 16/09/2017 | 16/09/2017 | [6 empty] | Not started | 24/10/2017 |  | Not started | [5 empty] | Not started | 2017-06-11 |  | Not started | 2017-07-11
|  | C.02 | Exception 1 | Low | Not started | 2017-09-10 |  | Not started | 20/09/2017 | [7 empty] | Not started | 24/10/2017 |  | Not started | [5 empty] | Not started | 2017-06-11 |  | Not started | 2017-07-11
Document date | Archive documentation | D | Introduce file archive data in the dedicated app | Low | Not started | 2017-09-10 |  | Not started | 20/09/2017 | [7 empty] | Not started | 24/10/2017 |  | Not started | [5 empty] | Not started | 2017-06-11 |  | Not started | 2017-07-11